## Project Tracker
MediAssist AI Capstone Project Tracker
Phase | Module | Description | Deliverables | Weight % | Status | Start Date | Target Date
1 | Requirements Understanding | Understand business problem, architecture, datasets, personas | Requirement understanding document | 5% | Not Started
2 | Solution Architecture | Create architecture diagrams, agent workflow, deployment design | Architecture breakdown document | 5% | Not Started
3 | Data Ingestion Pipeline | PDF parsing, image ingestion, chunking, metadata creation, embeddings | Working ingestion pipeline | 10% | Not Started
4 | Vector Database Setup | FAISS/ChromaDB indexing and storage | Indexed knowledge base | 5% | Not Started
5 | Enterprise RAG Pipeline | Semantic search, hybrid retrieval, citations, metadata filtering | Working RAG chatbot | 10% | Not Started
6 | MCP Server Development | Build MCP server, PostgreSQL connectors and tools | MCP Server with tools | 10% | Not Started
7 | MCP Agent Integration | Agent tool calling and PostgreSQL retrieval | Working structured retrieval | 5% | Not Started
8 | Multimodal AI | Prescription analysis, OCR, report extraction using BLIP/LLaVA | Vision processing module | 10% | Not Started
9 | Multi-Agent Orchestration | Planner, Retriever, MCP, Vision, Reasoning agents in LangGraph | LangGraph workflow | 15% | Not Started
10 | Reasoning & Response Generation | Context synthesis and grounded recommendations | Response generation module | 5% | Not Started
11 | Evaluation Framework | LLM-as-Judge, hallucination detection, retrieval evaluation | Evaluation dashboard | 10% | Not Started
12 | Frontend Development | Streamlit chat, uploads, history, dashboards | Working UI | 5% | Not Started
13 | Dockerization | Dockerfile, Docker Compose, container testing | Containerized solution | 2.5% | Not Started
14 | Azure Deployment | Deploy application to Azure Container Apps | Live deployment | 2.5% | Not Started
15 | Documentation & Demo | GitHub, technical docs, architecture docs, final demo | Final submission package | 5%